## Slide 1: Air traffic and logistics development between the EU rural areas and China

## Slide 2: Estonia - local partners overview
Main partners who have signed the Letter of Intent:
LAG Tartu County Development Association
Tartu City Government
Tartu Airport (Tallinn Airport)
Estonian Aviation Academy
Tartu University
Associated partners: Tartu Science Park, Tartu Business Advisory Services Foundation, Estonian Aviation Museum, Estonian Aviation Cluster, Tallinn Airport

## Slide 3: Project state of play in Estonia
1) Preparation of the WP 3 work with Estonian Aviation Academy, Tartu University and Pakker Avio.
Aviation Academy will take a lead organizing the work of the WP 3 in Estonia and in the project consortium.
Aviation Academy will evaluate the amount of the additional work to be done under WP 3.
TAS and Academy will agree on ToR.

## Slide 4: Project state of play in Estonia
2) Defining the partners to be involved into different WPs, agreed so far:
WP 2 (feasibility study) – Tartu University, Aviation Academy, Pakker Avio
WP 4 (business platforms) – Tartu City Government, LAG TAS, Business Advisory Centre, Science Park, Aviation Academy, Pakker Avio
WP 5 (tourism) – Tartu City Government, Tartu County Tourism Board, LAG TAS
In addition we will involve Estonian Aviation Cluster and Tallinn Airport.

## Slide 5: Work package 3 – 2020 activities
Task 1: Building the EU secondary airports training consortium and implementing trainings
Open call for project partners who would like to participate in the work of the WP 3 together with mapping their capacities and needs, fulfilling short baseline survey – February-April 2020
Designing the specification and work plan for the joint training program between European partners - April-June 2020
Letter of Intent between European members of the training consortium with joint targets towards developing aviation training capacities for European and Chinese partners – June 2020
Designing the joint training program – September 2020-March 2021

## Slide 6: Work package 3 - 2020 activities
Identifying corresponding partner from Chinese side to be partner for the European training consortium – May-June 2020
Identifying the rules and requirements from European and Chinese side to provide joint aviation training program in Europe – February-October 2020
Activating/conducting the certification process if needed – May 2020 - …
Signing corresponding agreements between European partners and with Chinese – September 2020 - …
2021 second half - the first test group training

## Slide 7: Work package 3 - 2020 activities
Task 2: Carrying out and testing innovative solutions related to robotics and automisation in secondary airports:
Mapping interested technology companies among WP partners to introduce their technologies related to the robotics and automisation – since September 2020
Collecting inputs from WP 2 about incubation plan – since September 2020
Drafting an incubation plan of the consortium – since September 2020

## Slide 8: Work package 3 - 2020 activities
Monitoring and evaluation of the progress of the WP 3
• Progress report at regular Zoom meetings – since March 2020
• Semiannual report will be provided to project partners at face-to-face meetings
Exploring the available funds and financing possibilities in Europe and China for further development of the project.
• Mapping of potential funds available for training consortium activities – since September 2020 (ERASMUS, etc)