## Slide 1: Air traffic and logistics development between the EU rural areas and China

## Slide 2: Work packages next steps until October 2020

## Slide 3: WP 1 - Coordination
1) Visit to Lesvos to meet Creek partners and clarify project activities | April
2) Finalizing consortium building (visit to Austria and Spain if needed) | 30.06
3) Taking offers to project visual identity (logo) and website | 09.04
4) Zoom meetings every second month | next Zoom 09.04
5) China visit preparation with Jukka | 18.-24.05
6) Face-to-face meeting in Greece, Lesvos | 06-09.10
7) Collecting budget inputs from partners and drafting the budget | Since March

## Slide 4: WP 2 – Feasibility study
1) Local partnerships established and defined the lead expert | 31.03
2) Call to project partners to send inputs for the feasibility study specification – what are the questions we need to find response through feasibility study and define common approach | April
3) To carry out feasibility study | Starting in July

## Slide 5: WP 3 – aviation training and incubations
1) Open call with short questionnaire to partners to define their training consortium partners and get overview about partners capacities | 01.03.-31.03
2) Designing work plan for building joint training program | April-June
3) Letter of Intent between training consortium partners | May
4) Drafting the joint training program | Since September
5) Identifying corresponding partner from Chinese side | April-May
6) Rules and requirements and certification process from European and Chinese side related to the training program | Since March
7) Mapping of partners and companies for incubation of innovative solutions in all partner airports | September

## Slide 6: WP 4 – business platforms
1) Business with China event where partners can be involved in online | March-April
2) Elisabet sends guidelines to partners for follow up | March-April
3) Partners start similar processes in their countries to identify business partners | March-June
4) Regular meetings with businesses, selecting businesses to work with Chinese, organize briefings, etc | Since June

## Slide 7: WP 5 - Tourism
1) Mapping of assets of partners - preparing the guidelines for partners and the questionnaire with the aim to gather the data about the assets, opportunities and challenges in tourism from the regions involved. | March-April
2) Partners gathering the data about tourist assets, capacities and trends in their regions. | May-June
3) Gathering the data and drafting the report, analysis of the potentials for development of rural tourism in the partnership around the TNC project. | July-August
4) Lead partner of WP 5 launches the call for provider of the research/study about the existing rural tourism platforms, networks and businesses in Europe (outsourcing). visitruraleurope.com | May-September
5) Based on the findings from the mapping of the assets (1.1.) designing of the few pilot tourist products, synchronized between involved partner’s regions (regional ITP). | June-October

## Slide 8: WP 6 – Work with Chinese
1) Prepare the study visit visa invitations and initial program. | March-April
2) Present the aviation training consortium to Chinese side via letter of intent. | May-June
3) Present the business partners to investment and incubation partners in China via USF platform model. | May-August
4) Propose a joint project for the Chinese side and engage negotiations and discussions. | May-September
5) Memorandum with Chinese side feasibility partner. | September-October