## Slide 1
AIR TRAFFIC AND LOGISTICS DEVELOPMENT BETWEEN THE EU RURAL AREAS AND CHINA
WORK PLAN WP2 – FEASIBILITY STUDY

## Slide 2
WP2
FEASIBILITY STUDY
WORK PLAN
WP Leader: LAG La Cittadella del Sapere (supported by PTSCLAS)
WHAT IS PTSCLAS EXPECTED TO DO?
Preparing the guidelines for carrying out the feasibility studies at local level
Providing technical assistance to the partner LAGs (meetings, emails, etc.)
PTSCLAS’ OUTPUTS
Guidelines (chapters 1 & 2 by already delivered*; chapters 3 & 4 by October 2020)
Recommendations for joint developments and linkages between partner airports and operations, flights, collaborations, etc
* To be validated

## Slide 3
WP2
FEASIBILITY STUDY
WORK PLAN
# | ACTIVITIES | RESPONSIBLE PARTNER(S) | JUL 2020 | AUG 2020 | SEP 2020 | OCT 2020 | NOV 2020 | DEC 2020 | JAN 2021 | FEB 2021 | MAR 2021 | NOTES
1 | DELIVERY OF THE LAG QUESTIONNAIRES TO THE WP2 LEADER | EE, FI, GR, IT, SI | X |  |  |  |  |  |  |  |  | Deadline: 03 July 2020 (missing: GR and SI)
2 | FEASIBILITY STUDY MANUAL: CONSULTATIONS WITH LOCAL STAKHOLDERS | EE, FI, GR, IT, SI | X | X |  |  |  |  |  |  |  | Deadline: 31 August 2020 (chapters 1 & 2)
3 | DELIVERY OF THE FINAL VERSION OF THE CHAPTERS 1 & 2 OF THE MANUAL | IT - WP LEADER (PTSCLAS) |  |  | X |  |  |  |  |  |  | Deadline: 30 September 2020
4 | COLLECTING INFO AT LOCAL LEVEL AND DRAFTING THE FEASIBILITY STUDIES (Ch. 1&2) | EE, FI, GR, IT, SI |  |  |  | X | X | X |  |  |  | Deadline: 30 November 2020 (postpone to December 2020?) PTSCLAS' individual assistance
5 | PREPARATION AND DELIVERY OF THE CHAPTERS 3 & 4 OF THE MANUAL | IT - WP LEADER (PTSCLAS) |  |  | X | X |  |  |  |  |  | 
6 | COLLECTING INFO AT LOCAL LEVEL AND DELIVERY THE FEASIBILITY STUDIES (Ch. 3&4) | EE, FI, GR, IT, SI |  |  |  |  | X | X |  |  |  | Final delivery by the 31 December 2020?
7 | ANALYSIS OF THE LOCAL FEASIBILITY STUDIES | IT - WP LEADER (PTSCLAS) |  |  |  |  |  |  | X |  |  | 
8 | RECOMMENDATIONS FOR JOINT DEVELOPMENTS AND LINKAGES BETWEEN PARTNER AIRPORTS AND OPERATIONS, FLIGHTS, COLLABORATIONS, ETC | IT - WP LEADER (PTSCLAS) |  |  |  |  |  |  | X |  |  | 
10 | OPEN EVENTS IN THE PARTNER COUNTRIES? | IT - WP LEADER (PTSCLAS) |  |  |  |  |  |  |  | X | X | Italian date to be decided. Italian open event with all the PPs?

## Slide 4
CONTACTS
LAG La Cittadella del Sapere
ADDRESS C.da Calda, Latronico (Pz) - Italy
Nicola Vita – Project Manager
vita@lacittadelladelsapere.it